## M4A_front
M4A front
| D |  |  |  | C |  |  |  | B |  |  |  | A
| Gas | Cables/ Noise | Top fix. / Grounding | Alignment | Gas | Cables/ Noise | Top fix. / Grounding | Alignment | Gas | Cables/ Noise | Top fix. / Grounding | Alignment | Gas | Cables/ Noise | Top fix. / Grounding | Alignment
Installation | R4 | PNB 93 | AR/FM | 20.4.07 | R4 | PNB 110 | AR/FM | 18.4.07 | R4 | PNB138 | FM/AR | 03.5.07 | R4 | PNB203 | FM/MV/AR | 26.4.07 | 32
32 | AR (6s) | GYGY | SF/GM |  | AR (6s) | GRGG | SF/GM |  | FM/AR(20s) | GGGG | SF/GM |  | AR (5s) | GYGG | SF/GM
| 25.4.07 | 31.05.07 | 04.07.07 |  | 17.4.07 | 31.05.07 | 04.07.07 |  | 03.5.07 | 31.05.07 | 04.07.07 |  | 26.7.04 | 31.05.07 | 04.07.07
| R4 | PNB 43 | AR/FM | 20.4.07 | R4 | PNB 148 | AR/FM | 18.4.07 | R4 | PNB038 | FM/AR | 03.5.07 | R4 | PNB144 | FM/MV/AR | 26.4.07 | 30
30 | AR (6s) | GGGG | SF/GM |  | AR (6s) | GGGY | SF/GM |  | FM/AR(22s) | GGGG | SF/GM |  | AR (6s) | GYGG | SF/GM
| 25.4.07 | 31.05.07 | 04.07.07 |  | 17.4.07 | 31.05.07 | 04.07.07 |  | 03.5.07 | 31.05.07 | 04.07.07 |  | 26.7.04 | 31.05.07 | 04.07.07
| R4 | PNB188 | MV/R | 24.4.07 | R4 | PNB 129 | AR/FM | 18.4.07 | R4 | PNB031 | FM/AR | 03.5.07 | R4 | PNB160 | FM/MV/AR | 26.4.07 | 28
28 | AR (5s) | GYGG | SF/GM |  | AR (6s) | GGGG | SF/GM |  | FM/AR(25s) | GYYG | SF/GM |  | AR (6s) | GYGG | SF/GM
| 25.4.07 | 1.06.07 | 04.07.07 |  | 17.4.07 | 1.06.07 | 04.07.07 |  | 03.5.07 | 1.05.07 | 04.07.07 |  | 26.4.07 | 1.05.07 | 04.07.07
| R4 | PNB194 | MV/R | 24.4.07 | R4 | PNB 66 | AR/FM | 18.4.07 | R4 | PNB183 | FM/AR | 03.5.07 | R4 | PNB166 | FM/MV/AR | 26.4.07 | 26
26 | AR (5s) | GYGY | SF/GM |  | AR (6s) | GGGG | SF/GM |  | FM/AR(23s) | GYYG | SF/GM |  | AR (6s) | GYGG | SF/GM
| 25.4.07 | 1.06.07 | 04.07.07 |  | 17.4.07 | 1.06.07 | 04.07.07 |  | 03.5.07 | 1.06.07 | 04.07.07 |  | 26.4.07 | 1.06.07 | 04.07.07
| R4 | PNB158 | MV/R | 24.4.07 | R4 | PNB 67 | AR/FM | 18.4.07 | R3 | FER 31 | AR/FM | 03.5.07 | R3 | FER 45 | AR/FM | 20.4.07 | 24
24 | AR (5s) | GGGY | SF/GM |  | AR (6s) | GGYG | SF/GM |  | FM/AR(20s) | CF | SF/GM |  | AR (7s) | CF | SF/GM
| 25.4.07 | 1.06.07 | 04.07.07 |  | 17.4.07 | 1.06.07 | 04.07.07 |  | 03.5.07 | 20/6/07 | 04.07.07 |  | 20.4.07 | 21/6/07 | 04.07.07
| R4 | PNB159 | FM/AR | 24.4.07 | R4 | PNB 147 | AR/FM | 18.4.07 | R3 | FER 09 | AR/FM | 03.5.07 | R3 | FER 40 | AR/FM | 20.4.07 | 22
22 | AR (5s) | GYYG | SF/GM |  | AR (8s) | GGYG | SF/GM |  | FM/AR(19s) | CF | SF/GM |  | AR (7s) | CF | SF/GM
| 25.4.07 | 1.06.07 | 04.07.07 |  | 17.4.07 | 1.06.07 | 04.07.07 |  | 03.5.07 | 20/6/07 | 04.07.07 |  | 20.4.07 | 21/6/07 | 04.07.07
| R4 | PNB062 | FM/AR | 24.4.07 | R4 | PNB 189 | AR/FM | 18.4.07 | R3 | FER19 | FM/AR | 03.5.07 |  |  |  |  | 20
20 | AR (5s) | GYGY | SF/GM |  | AR (6s) | GYYG | SF/GM |  | FM/AR(22s) | CF | SF/GM
| 25.4.07 | 1.06.07 | 04.07.07 |  | 17.4.07 | 1.06.07 | 04.07.07 |  | 03.5.07 | 21/6/07 | 04.07.07
| R4 | PNB156 | FM/AR | 24.4.07 | R4 | PNB 162 | AR/FM | 18.4.07 | R3 | FER06 | FM/AR | 03.5.07 |  |  |  |  | 18
18 | AR (6s) | GYGY | SF/GM |  | AR (6s) | GYGY | SF/GM |  | FM/AR(22s) | CF | SF/GM
| 25.4.07 | 1.06.07 | 04.07.07 |  | 17.4.07 | 1.06.07 | 04.07.07 |  | 03.5.07 | 20/6/07 | 04.07.07
See sheet for inner part
| R4 | PNB139 | FM/AR | 24.4.07 | R4 | PNB 98 | AR/FM | 19.4.07 | R3 | FER28 | FM/AR | 03.5.07
16 | AR (5s) | GYGG | SF/GM |  | AR (6s) | GGYG | SF/GM |  | FM/AR(25s) | CF | SF/GM
| 25.4.07 | 05.06.07 | 04.07.07 |  | 19.4.07 | 04.06.07 | 04.07.07 |  | 03.5.07 | 20/6/07 | 04.07.07
| R4 | PNB140 | FM/AR | 24.4.07 | R4 | PNB 157 | AR/FM | 19.4.07 | R3 | FER17 | FM/AR | 03.5.07
14 | AR (5s) | GYGG | SF/GM |  | AR (6s) | GRGG | SF/GM |  | FM/AR(23s) | CF | SF/GM
| 25.4.07 | 4.06.07 | 04.07.07 |  | 19.4.07 | 04.06.07 | 04.07.07 |  | 03.5.07 | 2007-05-07 | 04.07.07
| R4 | PNB181 | FM/AR | 24.4.07 | R4 | PNB 154 | AR/FM | 19.4.07 | R3 | FER55 | FM/AR | 26.4.07 | R3 | FER 14 | AR/FM | 20.4.07
12 | AR (5s) | GYGG | SF/GM |  | AR (6s) | GGYG | SF/GM |  | FM/AR(23s) | CF+AM | SF/GM |  | AR (8s) | CF+FE | SF/GM
| 25.4.07 | 4.06.07 | 04.07.07 |  | 19.4.07 | 4.06.07 | 04.07.07 |  | 03.5.07 | 2007-06-07 | 04.07.07 |  | 20.4.07 | 2007-10-07 | 04.07.07
| R4 | PNB134 | FM/AR | 24.4.07 | R4 | PNB 153 | AR/FM | 19.4.07 | R3 | FER03 | FM/AR | 26.4.07 | R3 | FER46 | FM/AR | 24.4.07
10 | FM/AR (5s) | GYYG | SF/GM |  | AR (5s) | GYGG | SF/GM |  | FM/AR(22s) | CF+AM | SF/GM |  | AR (6s) | FE | SF/GM
| 03.4.07 | 25.03.07 | 04.07.07 |  | 19.4.07 | 25.05.07 | 04.07.07 |  | 03.5.07 | 2007-04-07 | 04.07.07 |  | 26.4.07 | 2007-11-07 | 04.07.07
| R4 | PNB164 | FM/AR | 26.6.07 | R4 | PNB 30 | AR/FM | 19.4.07 | R4 | PNB099 | FM/AR | 03.4.07 | R4 | PNB136 | FM/MV/AR | 26.4.07
8 | FM/AR (20s) | GYGG | SF/GM |  | AR (5s) | GYGG | SF/GM |  | FM/AR(23s) | GGGG | SF/GM |  | AR (6s) | GYGG | SF/GM
| 03.4.07 | 25.05.07 | 04.07.07 |  | 19.4.07 | 25.05.07 | 04.07.07 |  | 03.5.07 | 29.05.07 | 04.07.07 |  | 26.4.07 | 25.05.07 | 04.07.07
| R4 | PNB170 | FM/AR | 26.4.07 | R4 | PNB 178 | AR/FM | 19.4.07 | R4 | PNB190 | FM/AR | 03.4.07 | R4 | PNB155 | FM/MV/AR | 26.4.07
6 | FM/AR(20s) | GYGG | SF/GM |  | AR (6s) | GYGG | SF/GM |  | FM/AR(22s) | GYGG | SF/GM |  | AR (5s) | GYYG | SF/GM
| 03.4.07 | 25.05.07 | 04.07.07 |  | 19.4.07 | 29.05.07 | 04.07.07 |  | 03.5.07 | 29.05.07 | 04.07.07 |  | 26.4.07 | 25.05.07 | 04.07.07
| R4 | PNB145 | FM/MV/AR | 26.4.07 | R4 | PNB 192 | AR/FM | 19.4.07 | R4 | PNB036 | FM/AR | 03.4.07 | R4 | PNB87 | FM/MV/AR | 26.4.07
4 | FM/AR(20s) | GYGG | SF/GM |  | AR (5s) | GYYG | SF/GM |  | FM/AR(23s) | GRGG | SF/GM |  | AR(6s) | GYGG | SF/GM
| 03.4.07 | 29.05.07 | 04.07.07 |  | 19.4.07 | 25.05.07 | 04.07.07 |  | 03.5.07 | 29.05.07 | 04.07.07 |  | 22.5.07 | 25.05.07 | 04.07.07
| R4 | PNB143 | (FM/MV/AR | 26.4.07 | R4 | PNB 196 | AR/FM | 19.4.07 | R4 | PNB135 | FM/AR | 03.4.07 | R4 | PNB177 | FM/MV/AR | 26.4.07
2 | FM/AR(20s) | GYGG | SF/GM |  | AR (6s) | GGGG | SF/GM |  | FM/AR(23s) | GYYG | SF/GM |  | AR(6s) | GYGG | SF/GM
| 03.4.07 | 25.05.07 | 04.07.07 |  | 19.4.07 | 25.05.07 | 04.07.07 |  | 03.5.07 | 29.05.07 | 04.07.07 |  | 22.5.07 | 24.05.07 | 04.07.07
Note on C6: GRGY: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- ERROR: iFEB:0 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE! ERROR: Possible changing between FEBs positions -> 01 and 02 CHECK BARCODE! ERROR: iFEB:2 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE! ----------------------------------------------------- ----- Charge Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:30 I2C:0 FEB:0 CH:04 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1891 WARNING: NodeID:30 I2C:0 FEB:0 CH:10 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 5344 WARNING: NodeID:30 I2C:0 FEB:0 CH:14 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 4991 WARNING: NodeID:30 I2C:0 FEB:0 CH:16 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1278 GYGY: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Charge Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:29 I2C:2 FEB:0 CH:04 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1182 WARNING: NodeID:29 I2C:2 FEB:0 CH:10 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 3409 WARNING: NodeID:29 I2C:2 FEB:0 CH:14 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 3589
Note on C7: LW-UP 0/3 SG M4A-UP-IB-9-24
Note on C11: LW-UP 1/0 SG M4C-UP-IB-9-14
Note on C14: Administrator: It looks like we need to change FEB 01! 1.06.07 FEB 01 4UE20900112297 replaced with 4UE20900113668 ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct 31.05.07 ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ERROR: NodeID:28 I2C:1 FEB:1 CH:10 Threshold(fC): 14.0 (Resbias(fC) = 5.0) Noise Rate(Hz): 14072 ERROR: NodeID:28 I2C:1 FEB:1 CH:14 Threshold(fC): 14.0 (Resbias(fC) = 5.0) Noise Rate(Hz): 1119 WARNING: NodeID:28 I2C:1 FEB:0 CH:03 Threshold(fC): 6.0 (Resbias = 5.0) Noise Rate(Hz): 1501 WARNING: NodeID:28 I2C:1 FEB:1 CH:10 Threshold(fC): 6.0 (Resbias = 5.0) Noise Rate(Hz): 8560 WARNING: NodeID:28 I2C:1 FEB:1 CH:14 Threshold(fC): 6.0 (Resbias = 5.0) Noise Rate(Hz): 1194
Note on C15: LW-UP 1/2 SG M4C-UP-IB-9-10
Note on C18: Administrator: WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Charge Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:28 I2C:1 FEB:0 CH:01 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1529
Note on C19: LW-UP 1/4 SG M4C-UP-IB-9-4
Note on C22: Administrator: WARNING: NodeID:28 I2C:2 FEB:0 CH:01 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1478 WARNING: NodeID:28 I2C:2 FEB:0 CH:03 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1113 WARNING: NodeID:28 I2C:2 FEB:0 CH:07 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 2097
Note on C23: LW-UP 1/6 SG M4C-UP-IB-8-24
Note on C26: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 184 +- 11
Note on C27: LW-UP 2/1 SG M4C-UP-IB-8-14
Note on C30: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Charge Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:28 I2C:2 FEB:0 CH:01 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1125
Note on C31: LW-UP 2/3 SG M4C-UP-IB-8-10
Note on C34: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Charge Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:29 I2C:0 FEB:0 CH:01 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 4073 WARNING: NodeID:29 I2C:0 FEB:0 CH:03 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 4187 WARNING: NodeID:29 I2C:0 FEB:0 CH:07 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 5640 WARNING: NodeID:29 I2C:0 FEB:0 CH:09 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1187 WARNING: NodeID:29 I2C:0 FEB:0 CH:11 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1601 WARNING: NodeID:29 I2C:0 FEB:0 CH:13 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1154
Note on C35: LW-UP 2/21 SG M4C-UP-IB-8-4
Note on C38: testuser: Odd behavior of the FE 0 Have to change it. Old FEB0: 4UE20900113901 New FEB0: 4UE20900112061 ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C39: LW-DW 3/9 SG M4C-DW-IB-8-3
Note on C42: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C43: LW-DW 3/31 SG M4C-DW-IB-8-9
Note on C46: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C47: LW-DW 4/13 SG M4C-DW-IB-8-13
Note on C50: testuser: WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 183 +- 10
Note on C51: LW-DW 4/23 SG M4C-DW-IB-8-23
Note on C54: testuser: ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C55: LW-DW 4/27 SG M4C-DW-IB-9-3
Note on C58: testuser: WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C59: LW-DW 4/29 SG M4C-DW-IB-9-9
Note on C62: testuser: no initialized 29.05.07 WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C63: LW-DW 4/31 SG M4C-DW-IB-9-13
Note on C66: testuser: WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C67: LW-DW 5/27 SG M4C-DW-IB-9-23
Note on H6: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- ERROR: iFEB:0 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE! ERROR: iFEB:1 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE!
Note on H7: LW-UP 0/2 SG M4C-UP-IB-9-8
Note on H10: Administrator: ----------------------------------------------------- ----- Charge Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:29 I2C:1 FEB:0 CH:01 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 2085
Note on H11: LW-UP 0/10 SG M4C-UP-IB-9-6
Note on H15: LW-UP 0/16 SG M4C-UP-IB-9-12
Note on H19: LW-UP 0/22 SG M4C-UP-IB-9-2
Note on H22: Administrator: ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 186 +- 10
Note on H23: LW-UP 0/30 SG M4C-UP-IB-8-8
Note on H26: Administrator: ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:28 I2C:2 FEB:2 CH:11 Estimated capacitance = 140 Cexp +- sigma = 179 +- 11 Channel estimated capacitance is out of range Estimated capacitance is lower than expected
Note on H27: LW-UP 1/15 SG M4C-UP-IB-8-6
Note on H30: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 193 +- 13
Note on H31: LW-UP 1/27 SG M4C-UP-IB-8-12
Note on H34: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Charge Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:28 I2C:2 FEB:0 CH:01 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1404 WARNING: NodeID:28 I2C:2 FEB:0 CH:03 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 2325 WARNING: NodeID:28 I2C:2 FEB:0 CH:07 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1217
Note on H35: LW-UP 2/20 SG M4C-UP-IB-8-2
Note on H38: testuser: ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 190 +- 13
Note on H39: LW-DW 3/8 SG M4C-DW-IB-8-1
Note on H42: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- ERROR: iFEB:0 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE!
Note on H43: LW-DW 3/30 SG M4C-DW-IB-8-11
Note on H46: testuser: ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 190 +- 12
Note on H47: LW-DW 4/12 SG M4C-DW-IB-8-5
Note on H50: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct
Note on H51: LW-DW 4/22 SG M4C-DW-IB-8-7
Note on H54: testuser: ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 184 +- 11
Note on H55: LW-DW 5/7 SG M4C-DW-IB-9-1
Note on H58: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on H59: LW-DW 5/13 SG M4C-DW-IB-9-11
Note on H62: testuser: ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ---- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:21 I2C:1 FEB:2 CH:11 Estimated capacitance = 132 Cexp +- sigma = 181 +- 14 Channel estimated capacitance is out of range Estimated capacitance is lower than expected
Note on H63: LW-DW 5/19 SG M4C-DW-IB-9-5
Note on H67: LW-DW 5/26 SG M4C-DW-IB-9-7
Note on M7: LW-UP 0/1 SG M4C-UP-IB-9-20
Note on M11: LW-UP 0/9 SG M4C-UP-IB-9-18
Note on M14: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 184 +- 11
Note on M15: LW-UP 0/15 SG M4C-UP-IB-8-20
Note on M18: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on M19: LW-UP 0/21 SG M4C-UP-IB-8-18
Note on M22: CF : GYGY <= 100 Hz @ 8 fC < 2.6 kHz @ 7 fC
Note on M26: CF : GYGY < 160 Hz @ 8 fC < 3 kHz @ 7 fC not worth to change FEB05 to get all ch. < 1 kHz @ 7 fC ----> result same with HV OFF
Note on M30: CF : GYGY < 100 Hz @ 8 fC <= 2 kHz @ 7 fC several ch. > kHz @ 7 fC
Note on M34: CF : GYGY < 170 Hz @ 8 fC < 4 kHz @ 7 fC ~ 6 channels > 1 kHz @ 7 fC ----> result same with HV OFF
Note on M38: CF : GYGG < 0.1 Hz @ 8 fC < 70 Hz @ 7 fC
Note on M42: CF : GYGY problem in TB (IB slot 5 connector 5) solved by Nikolai < 40 Hz @ 8 fC ; < 1.4 kHz @ 7 fC
Note on M45: LV-4 (10/11) IB-6 (1/3/2)
Note on M46: CF : GYGY < 150 Hz @ 8 fC 3 ch. > kHz @ 7 fC < 3 kHz @ 7 fC
Note on M50: CF : GYGY (Version $.2) <=200 Hz @ 8 fC ; <= 4 kHz @ 7 fC
Note on M54: testuser: no initialized
Note on M55: LW-DW 4/26 SG M4C-DW-IB-8-17
Note on M58: testuser: no initialized - fixed WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on M59: LW-DW 5/12 SG M4C-DW-IB-8-19
Note on M62: testuser: injection test failed Reason - signal cable swaped with M4R4 2B - Fixed ERROR: iFEB:0 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE!
Note on M63: LW-DW 5/18 SG M4C-DW-IB-9-17
Note on M66: testuser: injection test failed Reason : Signal cable swaped with M4R4 4B - Fixed GYYG WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 190 +- 12
Note on M67: LW-DW 5/25 SG M4C-DW-IB-9-19
Note on R6: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R7: LW-UP 0/0 SG M4C-UP-IB-9-22
Note on R10: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R11: LW-UP 0/8 SG M4C-UP-IB-9-16
Note on R14: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R15: LW-UP 0/14 SG M4C-UP-IB-8-22
Note on R18: Administrator: Power cable was disconnected
Note on R19: LW-UP 0/20 SG M4C-UP-IB-8-16
Note on R22: CF : GRGG < 30 Hz @ 8 fC < 700 Hz @ 7 fC
Note on R26: CF : GYGY < 120 Hz @ 8 fC < 3 kHz @ 7 fC
Note on R45: LV-4 (8/9) IB-5 (13/15/14)
Note on R46: GYGY <140Hz @ 8fC <3.7KHz @7fC 10 CH >KHz @ 7fC
Note on R49: LV-5 (0/1) IB-6 (13/15/14)
Note on R50: GYGY <208Hz @ 8fC <4KHz @7fC 5 CH >KHz @ 7fC
Note on R54: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Charge Analysis Diagnostics ----------------------------------------------------- ERROR: NodeID:21 I2C:1 FEB:0 CH:07 Threshold(fC): 14.0 (Resbias(fC) = 5.0) Noise Rate(Hz): 1755 ERROR: NodeID:21 I2C:1 FEB:0 CH:10 Threshold(fC): 14.0 (Resbias(fC) = 5.0) Noise Rate(Hz): 2281 .......................... WARNING: NodeID:21 I2C:1 FEB:0 CH:15 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 12207 WARNING: NodeID:21 I2C:1 FEB:0 CH:16 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 19650
Note on R55: LW-DW 5/6 SG M4C-DW-IB-8-15
Note on R58: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:21 I2C:0 FEB:2 CH:12 Estimated capacitance = 142 Cexp +- sigma = 181 +- 12 Channel estimated capacitance is out of range Estimated capacitance is lower than expected
Note on R59: LW-DW 5/11 SG M4C-DW-IB-8-21
Note on R62: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R63: LW-DW 5/17 SG M4C-DW-IB-9-15
Note on R66: testuser: WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R67: LW-DW 5/24 SG M4C-DW-IB-9-21

## M4A_back
M4A back
| A |  |  |  | B |  |  |  | C |  |  |  | D
| Gas | Cables/ Noise | Top fix. / Grounding | Alignment | Gas | Cables/ Noise | Top fix. / Grounding | Alignment | Gas | Cables/ Noise | Top fix. / Grounding | Alignment | Gas | Cables/ Noise | Top fix. / Grounding | Alignment
Installation | R4 | PNP 100 | AR/FM | 12.4.07 | R4 | PNP 193 | FM/AR | 9.5.07 | R4 | PNP 184 | AR/FM | 13.4.07 | R4 | PNP198 | S+G | 03.5.07
31 | AR (9s) | GYGG | SF/GM | KM/RW/TS | F/A(24s) | GRYG | SF/GM | KM | AR (9s) | GYGR | SF/GM | KM | GG/RW(15s) | GYGR | SF/GM | KM | 31
| 12.4.07 | 29.05.07 | 04.07.07 | 6.8.07 | 10.5.07 | 29.05.07 | 04.07.07 | 2.8.07 | 13.4.07 | 29.05.07 | 04.07.07 | 3.8.07 | 19.6.2007 | 29.05.07 | 04.07.07 | 1.8.07
| R4 | PNP 90 | AR/FM | 12.4.07 | R4 | PNP 128 | FM/AR | 9.5.07 | R4 | PNP 96 | AR/FM | 13.4.07 | R4 | PNP161 | S+G | 03.5.07
29 | AR (9s) | GYGG | SF/GM | KM/RW/TS | F/A(24s) | GGGG | SF/GM | KM | AR (9s) | GYYY | SF/GM | KM | GG/RW(21s) | GYYG | SF/GM | KM | 29
| 12.4.07 | 30.05.07 | 04.07.07 | 6.8.07 | 10.5.07 | 30.05.07 | 04.07.07 | 2.8.07 | 13.4.07 | 30.05.07 | 04.07.07 | 3.8.07 | 19.6.2007 | 30.05.07 | 04.07.07 | 1.8.07
| R4 | PNP 68 | AR/FM | 12.4.07 | R4 | PNP 195 | FM/AR | 9.5.07 | R4 | PNP 122 | AR/FM | 13.4.07 | R4 | PNP014 | S+G | 03.5.07
27 | AR (9s) | GGGG | SF/GM | KM/RW/TS | F/A(23s) | GYGG | SF/GM | KM | AR (13s) | GYGG | SF/GM | KM | GG/RW(15s) | GYGG | SF/GM | KM | 27
| 12.4.07 | 30.05.07 | 04.07.07 | 6.8.07 | 10.5.07 | 30.05.07 | 04.07.07 | 2.8.07 | 13.4.07 | 30.05.07 | 04.07.07 | 3.8.07 | 19.6.2007 | 31.05.07 | 04.07.07 | 1.8.07
| R4 | PNP 127 | AR/FM | 12.4.07 | R4 | PNP 191 | FM/AR | 10.5.07 | R4 | PNP 95 | AR/FM | 13.4.07 | R4 | PNP171 | S+G | 03.5.07
25 | AR (9s) | GYGG | SF/GM | KM/RW/TS | F/A(25s) | GGGG | SF/GM | KM | AR (9s) | GYGG | SF/GM | KM | GG/RW(15s) | GYGG | SF/GM | KM | 25
| 12.4.07 | 31.05.07 | 04.07.07 | 6.8.07 | 10.5.07 | 31.05.07 | 04.07.07 | 2.8.07 | 13.4.07 | 31.05.07 | 04.07.07 | 3.8.07 | 19.6.2007 | 31.05.07 | 04.07.07 | 1.8.07
| R3 | FER 23 | AR/FM | 10.5.07 | R3 | FER 18 | FM/AR | 9.5.07 | R4 | PNP 101 | AR/FM | 13.4.07 | R4 | PNP185 | S+G | 03.5.07
23 | F/A(50s) | CF-WB | SF/GM | KM/RW/TS | F/A(35s) | CF+WB | SF/GM | KM | AR (9s) | GYGG | SF/GM | KM | GG/RW12s) | GYGY | SF/GM | KM | 23
| 10.5.07 | 21/06/07 | 04.07.07 | 6.8.07 | 10.5.07 | 22/6/07 | 04.07.07 | 2.8.07 | 13.4.07 | 30.05.07 | 04.07.07 | 3.8.07 | 19.6.2007 | 30.05.07 | 04.07.07 | 1.8.07
| R3 | FER 37 | AR/FM | 10.5.07 | R3 | FER 43 | FM/AR | 10.5.07 | R4 | PNP 119 | AR/FM | 13.4.07 | R4 | PNP167 | S+G | 03.5.07
21 | F/A(40s) | CF-WB | SF/GM | KM/RW/TS | F/A(34s) | CF+WB | SF/GM | KM | AR (9s) | GYYG | SF/GM | KM | GG/RW(12s) | GYGY | SF/GM | KM | 21
| 10.5.07 | 21/06/07 | 04.07.07 | 6.8.07 | 10.5.07 | 22/6/07 | 04.07.07 | 2.8.07 | 13.4.07 | 31.05.07 | 04.07.07 | 3.8.07 | 19.6.2007 | 30.05.07 | 04.07.07 | 1.8.07
[5 empty] | R3 | FER 52 | FM/AR | 9.5.07 | R4 | PNP 97 | AR/FM | 16.4.07 | R4 | PNP187 | S+G | 03.5.07
19 |  | ` |  |  | F/A(32s) | CF+WB | SF/GM | KM | AR (9s) | GYYG | SF/GM | KM | GG/RW(11s) | GYGG | SF/GM | KM | 19
[5 empty] | 10.5.07 | 22/6/07 | 04.07.07 | 2.8.07 | 16.4.07 | 31.05.07 | 04.07.07 | 3.8.07 | 19.6.2007 | 31.05.07 | 04.07.07 | 1.8.07
[5 empty] | R3 | FER 53 | FM/AR | 9.5.07 | R4 | PNP 180 | AR/FM | 16.4.07 | R4 | PNP149 | S+G | 03.5.07
17 |  |  |  |  | F/A(32s( | CF+WB | SF/GM | KM | AR (9s) | GYGG | SF/GM | KM | GG/RW(12s) | GYGY | SF/GM | KM | 17
[5 empty] | 10.5.07 | 22/6/07 | 04.07.07 | 2.8.07 | 16.4.07 | 31.05.07 | 04.07.07 | 3.8.07 | 19.6.2007 | 31.05.07 | 04.07.07 | 1.8.07
See sheet for inner part
[5 empty] | R3 | FER 56 | FM/AR | 9.5.07 | R4 | PNP 152 | AR/FM | 16.4.07 | R4 | PNP169 | S+G | 03.5.07
15 |  |  |  |  | AA/AR(12s) | CF | SF/GM | KM | AR (9s) | GYGG | SF/GM | KM | FM(42s) | GYGG | SF/GM | KM
[5 empty] | 10.7.07 | 2007-06-07 | 04.07.07 | 2.8.07 | 16.4.07 | 05.06.07 | 04.07.07 | 3.8.07 | 18.5.07 | 05.06.07 | 04.07.07 | 1.8.07
[5 empty] | R3 | FER 47 | AS/AR | 5.5.07 | R4 | PNB 88 | AR/FM | 16.4.07 | R4 | PNP199 | S+G | 03.5.07
13 |  |  |  |  | AA/AR(11s) | CF+FE |  | KM | AR (9s) | GYGG | SF/GM | KM | FM(42s) | GYGG | SF/GM | KM
[5 empty] | 10.7.07 | 2007-10-07 |  | 2.8.07 | 16.4.07 | 05.06.07 | 04.07.07 | 3.8.07 | 18.5.07 | 05.06.07 | 04.07.07 | 1.8.07
| R3 | FER20 | FM/MV/AR | 27.4.07 | R3 | FER 21 | AS/AR | 5.7.07 | R4 | PNB 150 | AR/FM | 16.4.07 | R4 | PNB146 | FM/MV | 27.4.07
11 | FM(24s) | CF+FE | SF/GM | KM/RW/TS | AA/AR(11s) | CF |  | KM | AR (9s) | GGGG | SF/GM | KM | FM(50s) | GYGG | SF/GM | KM
| 18.5.07 | 2007-10-07 | 04.07.07 | 6.8.07 | 10.7.07 | 2007-06-07 |  | 2.8.07 | 16.4.07 | 05.06.07 | 04.07.07 | 3.8.07 | 18.5.07 | 05.06.07 | 04.07.07 | 1.8.07
| R3 | FER22 | FM/MV/AR | 27.4.07 | R3 | FER 41 | AS/AR | 5.7.07 | R4 | PNB 156 | AR/FM | 16.4.07 | R4 | PNB174 | FM/MV | 27.4.07
9 | FM(25s) | CF+FE | SF/GM | KM/RW/TS | AA/AR(11s) | CF |  | KM | AR (9s) | GYGG | SF/GM | KM | FM(36s) | GYGG | SF/GM | KM
| 18.5.07 | 2007-10-07 | 04.07.07 | 6.8.07 | 10.7.07 | 2007-06-07 |  | 2.8.07 | 16.4.07 | 05.06.07 | 04.07.07 | 3.8.07 | 18.5.07 | 05.06.07 | 04.07.07 | 1.8.07
| R4 | PNB182 | FM/MV/AR | 27.4.07 | R4 | PNB182 | SG/GM | 04.06.07 | R4 | PNB 176 | AR/FM | 16.4.07 | R4 | PNB173 | FM/MV | 27.4.07
7 | FM(75s) | GYGG | SF/GM | KM/RW/TS | AA/AR(20s) | GYGG | SF/GM | KM | AR (8s) | GYGG | SF/GM | KM | FM(33s) | GYGG | SF/GM | KM
| 18.5.07 | 04.06.07 | 04.07.07 | 6.8.07 | 10.7.07 | 05.06.07 | 04.07.07 | 2.8.07 | 16.4.07 | 04.06.07 | 04.07.07 | 3.8.07 | 18.5.07 | 04.06.07 | 04.07.07 | 1.8.07
| R4 | PNB179 | FM/MV/AR | 27.4.07 | R4 | PNB204 | SG/GM | 04.06.07 | R4 | PNP 41 | AR/FM | 16.4.07 | R4 | PNB202 | SG/GM | 04.5.07
5 | FM(75s) | GYGG | SF/GM | KM/RW/TS | AA/AR(21s) | GYGY | SF/GM | KM | AR (8s) | GGRG | SF/GM | KM | FM(27s) | GYGG | SF/GM | KM
| 18.5.07 | 07.06.07 | 04.07.07 | 6.8.07 | 10.7.07 | 05.06.07 | 04.07.07 | 2.8.07 | 16.4.07 | 1.06.07 | 04.07.07 | 3.8.07 | 18.5.07 | 1.06.07 | 04.07.07 | 1.8.07
| R4 | PNB163 | FM/MV/AR | 27.4.07 | R4 | PNB151 | SG/GM | 04.06.07 | R4 | PNB175 | FM/MV/AR | 27.4.06 | R4 | PNB109 | SG/GM | 04.5.07
3 | FM(100s) | GYGG | SF/GM | KM/RW/TS | AA/AR(24s) | GYYG | SF/GM | KM | FM(7s) | GYGG | SF/GM | KM | FM(30s) | GYGG | SF/GM | KM
| 18.5.07 | 1.06.07 | 04.07.07 | 6.8.07 | 10.7.07 | 05.06.07 | 04.07.07 | 2.8.07 | 18.5.07 | 1.06.07 | 04.07.07 | 3.8.07 | 18.5.07 | 1.06.07 | 04.07.07 | 1.8.07
| R4 | PNB 207 | OM | 09.05.08 | R4 | PNB 205 | OM | 09.05.08 | R4 | PNB 209 | OM | 09.05.08 | R4 | PNB 208 | OM | 09.05.08
1 | OM(15s) |  | OM |  | OM(13s) |  | OM |  | OM(14s) |  | OM |  | OM(14s) |  | OM
| 16.5.08 |  | 16.05.08 |  | 16.5.08 |  | 16.05.08 |  | 16.5.08 |  | 16.05.08 |  | 16.5.08 |  | 16.05.08
Note on C6: Administrator: WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C7: LW-UP 0/4 SG M4C-UP-IB-9-21
Note on C10: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C11: LW-UP 0/11 SG M4C-UP-IB-9-15
Note on C15: LW-UP 0/17 SG M4C-UP-IB-8-21
Note on C18: Administrator: ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C19: LW-UP 0/23 SG M4C-UP-IB-8-15
Note on C22: CF :GYGY <90Hz @ 8fC <2kHz@7fC
Note on C26: CF : GYGY < 120 Hz @ 8 fC < 2200 Hz @ 7 fC
Note on C45: LV-4 (14/15) IB-5 (24/22/23)
Note on C46: GYYY <220Hz @ 8fC <4.2KHz @7fC 6 CH >KHz @ 7fC
Note on C49: LV-5 (2/3) IB-6 (24/22/23)
Note on C50: GYGY <100Hz @ 8fC <1.6KHz @7fC 5 CH >KHz @ 7fC
Note on C54: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C55: LW-DW 5/8 SG M4C-DW-IB-8-16
Note on C58: testuser: Need to replace SPB --> fixed ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- ERROR: NodeID:21 I2C:2 FEB:1 CH:09 Estimated capacitance = 0 Cexp +- sigma = 184 +- 30 Open Channel old FEB1:4UE20900113745 new FEB1:4UE20900111349 ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C59: LW-DW 5/14 SG M4C-DW-IB-8-22
Note on C62: testuser: FEB 02 changed for 4UE20900112082 ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on C63: LW-DW 5/20 SG M4C-DW-IB-9-16
Note on C67: LW-DW 5/28 SG M4C-DW-IB-9-22
Note on H6: Administrator: ERROR: iFEB:1 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE! WARNING: NodeID:28 I2C:2 FEB:0 CH:03 Estimated capacitance = 106 Cexp +- sigma = 174 +- 21 Channel estimated capacitance is out of range Estimated capacitance is lower than expected
Note on H7: LW-UP 0/5 SG M4C-UP-IB-9-19
Note on H10: Administrator: Signal cable shorted to ground - no covers on the TB's, Noisolation film on the TB's Fixed on the TB8 and TB9.
Note on H11: LW-UP 0/12 SG M4C-UP-IB-9-17
Note on H14: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on H15: LW-UP 0/18 SG M4C-UP-IB-8-19
Note on H19: LW-UP 0/24 SG M4C-UP-IB-8-17
Note on H22: CF : GYGY < 70 Hz @ 8 fC < 2 kHz @ 7 fC
Note on H26: CF : GYGY < 80 Hz @ 8 fC < 2.1 kHz @ 7 fC
Note on H30: CF : GYGY ---> changed FEB01 < 70 Hz @ 8 fC (2 kV) < 2 kHz @ 7 fC (2kV)
Note on H34: CF : GYGG < 20 Hz @ 8 fC (2 kV) < 600 Hz @ 7 fC (2kV)
Note on H37: LV-3 (20/21) IB-5(12/10/11)
Note on H38: CF : RYGY several ch. of FEB2 with DIALOG > 510 < 50 Hz @ 8 fC ; < 1.5 kHz @ 7 fC
Note on H41: LV-4 (4/5) IB-5(9/7/8)
Note on H42: GYGY <162Hz @ 8fC <3.6KHz @7fC 10 CH >KHz @ 7fC
Note on H45: LV-4 (16/17) IB-6(12/10/11)
Note on H46: CF : GYGY < 200 Hz @ 8 fC ; < 3 kHz @ 7 fC
Note on H49: LV-5 (4/5) IB-6(9/7/8)
Note on H50: CF : GYGY < 100 Hz @ 8 fC ; < 1.8 kHz @ 7 fC
Note on H54: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on H55: LW-DW 5/9 SG M4C-DW-IB-8-18
Note on H58: testuser: ---------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on H59: LW-DW 5/15 SG M4C-DW-IB-8-20
Note on H62: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:21 I2C:1 FEB:0 CH:09 Estimated capacitance = 127 Cexp +- sigma = 183 +- 16 Channel estimated capacitance is out of range Estimated capacitance is lower than expected
Note on H63: LW-DW 5/21 SG M4C-DW-IB-9-18
Note on H67: LW-DW 5/29 SG M4C-DW-IB-9-20
Note on M6: Administrator: WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ERROR: NodeID:28 I2C:2 FEB:0 CH:01 Threshold(fC): 14.0 (Resbias(fC) = 5.0) Noise Rate(Hz): 6252 ...... ..... ...... WARNING: NodeID:28 I2C:2 FEB:0 CH:16 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 3153 IF THE CONTROL CABLE GROUND DISCONECTED CHAMBER IS OK
Note on M7: LW-UP 0/6 SG M4C-UP-IB-9-7
Note on M10: Administrator: WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 183 +- 11 WARNING: NodeID:29 I2C:0 FEB:0 CH:01 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1931
Note on M11: LW-UP 0/13 SG M4C-UP-IB-9-5
Note on M14: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on M15: LW-UP 0/19 SG M4C-UP-IB-9-11
Note on M18: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on M19: LW-UP 0/25 SG M4C-UP-IB-9-1
Note on M22: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct
Note on M23: LW-UP 0/31 SG M4C-UP-IB-8-7
Note on M26: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 184 +- 11
Note on M27: LW-UP 1/20 SG M4C-UP-IB-8-5
Note on M30: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 188 +- 12
Note on M31: LW-UP 2/6 SG M4C-UP-IB-8-11
Note on M34: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on M35: LW-UP 2/30 SG M4C-UP-IB-8-1
Note on M38: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on M39: LW-DW 3/22 SG M4C-DW-IB-8-2
Note on M42: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct
Note on M43: LW-DW 4/6 SG M4C-DW-IB-8-12
Note on M47: LW-DW 4/18 SG M4C-DW-IB-8-6
Note on M50: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct
Note on M51: LW-DW 4/24 SG M4C-DW-IB-8-8
Note on M54: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on M55: LW-DW 5/10 SG M4C-DW-IB-9-2
Note on M58: testuser: ------------------------------------------------------ ----- Noise Analysis Diagnostics ----------------------------------------------------- ERROR: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 191 +- 9
Note on M59: LW-DW 5/16 SG M4C-DW-IB-9-12
Note on M62: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on M63: LW-DW 5/22 SG M4C-DW-IB-9-6
Note on M67: LW-DW 5/30 SG M4C-DW-IB-9-8
Note on R6: Administrator: WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ERROR: NodeID:28 I2C:2 FEB:0 CH:01 Threshold(fC): 14.0 (Resbias(fC) = 5.0) Noise Rate(Hz): 25053 .... ..... ..... ERROR: NodeID:28 I2C:2 FEB:0 CH:13 Threshold(fC): 14.0 (Resbias(fC) = 5.0) Noise Rate(Hz): 1824
Note on R7: LW-UP 0/7 SG M4C-UP-IB-9-23
Note on R10: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: High Capacitance Average respect to ExpCap Expected capacitance = 160 Cexp +- sigma = 184 +- 11
Note on R11: LW-UP 1/1 SG M4C-UP-IB-9-13
Note on R14: Administrator: Injection test fiailed. FEB1, FEB2 FEB02 CH13: counters-> DIALOG=16777215 ACQ=1842827 FEB02 CH14: counters-> DIALOG=16777215 ACQ=2426416 FEB02 CH15: counters-> DIALOG=16777215 ACQ=1130672 Fixed. Bad connection on the chamber side. 31.05.07 ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R15: LW-UP 1/3 SG M4C-UP-IB-9-9
Note on R18: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R19: LW-UP 1/5 SG M4C-UP-IB-9-3
Note on R22: Administrator: WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct WARNING: NodeID:28 I2C:2 FEB:0 CH:01 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1109
Note on R23: LW-UP 2/0 SG M4C-UP-IB-8-23
Note on R26: Administrator: WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct WARNING: NodeID:28 I2C:2 FEB:0 CH:01 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 2504 WARNING: NodeID:28 I2C:2 FEB:0 CH:03 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 6241 WARNING: NodeID:28 I2C:2 FEB:0 CH:07 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 4940 WARNING: NodeID:28 I2C:2 FEB:0 CH:11 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1051
Note on R27: LW-UP 2/2 SG M4C-UP-IB-8-13
Note on R30: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R31: LW-UP 2/7 SG M4C-UP-IB-8-9
Note on R34: Administrator: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Charge Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:29 I2C:1 FEB:0 CH:03 Threshold(fC): 12.0 (Resbias = 5.0) Noise Rate(Hz): 1037
Note on R35: LW-UP 2/31 SG M4C-UP-IB-8-3
Note on R38: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct
Note on R39: LW-DW 3/23 SG M4C-DW-IB-8-4
Note on R42: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R43: LW-DW 4/7 SG M4C-DW-IB-8-10
Note on R46: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R47: LW-DW 4/19 SG M4C-DW-IB-8-14
Note on R50: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R51: LW-DW 4/25 SG M4C-DW-IB-8-24
Note on R54: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R55: LW-DW 4/28 SG M4C-DW-IB-9-4
Note on R58: testuser: ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct
Note on R59: LW-DW 4/30 SG M4C-DW-IB-9-10
Note on R62: ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct
Note on R63: LW-DW 5/23 SG M4C-DW-IB-9-14
Note on R67: LW-DW 5/31 SG M4C-DW-IB-9-24

## M4A_IP_front
M4A inner part front
| A3 |  |  |  |  | A2 |  |  |  | A1
| Gas | Cables/ Noise | Top fix. / Grounding | Alignment |  | Gas | Cables/ Noise | Top fix. / Grounding | Alignment | Gas | Cables/ Noise | Top fix. / Grounding | Alignment
Installation | R2 | FER005 | FM/AR | 23.4.07 | [5 empty] | R2 | FER020 | FM/AR | 23.4.076
20 | AR(6s) | 22/06/07 | SF/GM | [6 empty] | AR (6s) | 22/06/07 | SF/GM
| 24.4.07 | WB | 04.07.07 | [6 empty] | 24.4.07 | WB | 04.07.07
| R2 | FER016 | FM/AR | 23.4.07 |  | R1 | CER10 | FM/AR | 10.5.07 | R1 | CER15 | FM/AR | 10.5.07
18 | AR (7s) | 22/06/07 | SF/GM |  |  | F/A(7s) | KM | SF/GM |  | AA/AR(7s) | KM | SF/GM
| 24.4.07 | WB | 04.07.07 |  |  | 25.5.07 | 18.6.07 | 04.07.07 |  | 2007-12-07 | 18.6.07 | 04.07.07
| R2 | FER012 | FM/AR | 23.4.07 |  | R1 | CER13 | FM/AR | 13.5.07
16 | AR(7s) | CF+NB | SF/GM |  |  | F/A(7s) | KM | SF/GM |  |  | beam pipe hole
| 24.4.07 | 2007-09-07 | 04.07.07 |  |  | 25.5.07 | 14.6.07 | 04.07.07
ECS1 and ECS2 swapped, labels corrected
| R2 | FER004 | FM/AR | 23.4.07 |  | this chamber was removed and re-installed |  |  |  | R2 | FER008 | FM/AR | 23.4.07
14 | AR (7s) | OM | SF/GM |  |  | due to a wrong balcony position (KM, 3.8.07) |  |  |  | AR (6s) | OM | SF/GM
| 24.4.07 | 18.06.07 | 04.07.07 | [6 empty] | 24.4.07 | 18.06.07 | 04.07.07
`
Note on C6: WB: GYYY WAR ~ 5-600 Hz in few ch (FEB 3 ch 10 and FEB4 ch 10) @ 8fC ~3 kHz @ 7fC the whole chamber is a little noisy
Note on C10: WB: GYGY GOOD < 50 Hz @ 8 fC < 2kHz @ 7 fC note: the cables of FEB 1 and 2 are swapped on the TB --> put in the correct position
Note on C13: LV-3 (4/5) IB-3 (13/14/15/22/23/24)
Note on C14: CF : GYRY TB repaired by Nikolai : FEB0 ch.11-12 bad contact ---> re-soldered FEB5 ch.3-4 broken pin in crate --> repaired < 100 Hz @ 8 fC ; < 3.5 kHz @ 7 fC (4 ch. > kHz)
Note on C18: GYGY ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:3 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:4 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:5 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Charge Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:21 I2C:0 FEB:1 CH:11 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 1484 WARNING: NodeID:21 I2C:0 FEB:3 CH:07 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 1538 WARNING: NodeID:21 I2C:0 FEB:4 CH:10 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 4773 WARNING: NodeID:21 I2C:0 FEB:5 CH:02 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 1576 WARNING: NodeID:21 I2C:0 FEB:5 CH:06 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 2301 WARNING: NodeID:21 I2C:0 FEB:5 CH:08 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 2737 WARNING: NodeID:21 I2C:0 FEB:5 CH:10 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 2972 WARNING: NodeID:21 I2C:0 FEB:5 CH:12 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 2288 WARNING: NodeID:21 I2C:0 FEB:5 CH:14 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 3165 WARNING: NodeID:21 I2C:0 FEB:5 CH:16 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 7877
Note on C19: LV 3/26,27 M4A-DW-IB-2-13,14,15,22,23,24
Note on H10: 1st half (FEB00-05): GYYG WARNING: iFEB:5 -> Barcode not found in database ----------------------------------------------------- ----- Noise Analysis Diagnostics WARNING: NodeID:28 I2C:1 FEB:0 CH:13 Estimated capacitance = 89 Cexp +- sigma = 54 +- 11 Channel estimated capacitance is out of range Estimated capacitance is higher than expected noise: 5fC: FEB00: <10^4 Hz, all others: <10^3Hz 6fC: Hz: FEB00: 10Hz, all others: 0Hz 7fC: all 0Hz 2nd half (FEB06-11): GYGG WARNING: iFEB:5 -> Barcode not found in database noise: 5fC: 10^2 Hz 6fC: 0Hz
Note on H14: ECS1 and 2 swapped on chamber side -> correct labels 1st half (FEB00-FEB05): GGGG noise rate: 5fC: <10^3 Hz 6fC: ~0 Hz 2nd half (FEB01-FEB11): GYGG noise rate: 5fC: <10^2Hz
Note on M6: WB: GYGY OK < 100 Hz @ 8fC <3 kHz @ 7 fC
Note on M10: 1st half (FEB00-05): GYGG WARNING: iFEB:5 -> Barcode not found in database noise: 5fC: 10^2Hz 6fC: 0Hz 2nd half (FEB06-11): GYGG All SG cables were connected to the chamber in reverse order. Now O.K. WARNING: iFEB:5 -> Barcode not found in database noise: 5fC: 10^3Hz (FEB02), all others 10^2Hz 6fC: 10 Hz (FEB02), all others: 0Hz
Note on M18: GYGY ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:3 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:4 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:5 -> Barcode not found in database please confirm if barcode is correct ----------------------------------------------------- ----- Charge Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:21 I2C:0 FEB:0 CH:13 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 1412 WARNING: NodeID:21 I2C:0 FEB:2 CH:07 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 2944 WARNING: NodeID:21 I2C:0 FEB:2 CH:10 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 1552 WARNING: NodeID:21 I2C:0 FEB:2 CH:13 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 1044 WARNING: NodeID:21 I2C:0 FEB:3 CH:10 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 1716 WARNING: NodeID:21 I2C:0 FEB:4 CH:10 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 1511 WARNING: NodeID:21 I2C:0 FEB:5 CH:10 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 8197
Note on M19: LV 3/24,25 M4A-DW-IB-1-13,14,15,22,23,24

## M4A_IP_back
M4A inner part back
| A1 |  |  |  | A2 |  |  |  | A3
| Gas | Cables/ Noise | Top fix. / Grounding | Alignment | Gas | Cables/ Noise | Top fix. / Grounding | Alignment | Gas | Cables/ Noise | Top fix. / Grounding | Alignment
Installation | R2 | FER29 | S+G | 03.5.07 |  |  |  |  | R2 | FER27 | S+G | 03.5.07
19 | F/A(16s) | CF | SF/GM | KM/TS/RW |  |  |  |  | F/A(34s) | CF | SF/GM | KM/RW
| 21.5.07 | 19/6/07 | 04.07.07 | 1.8.07 | this chamber was removed and re-installed |  |  |  | 21.5.07 | 19/6/07 | 04.07.07 | 6.8.07
due to a wrong balcony position (KM, 3.8.07)
[5 empty] | R1 | CER16 | FM/AR | 9.5.07 | R2 | FER09 | MV/RM | 22.4.07
17 |  | beam pipe hole |  |  | F/A(16s) | KM, RW | SF/GM | KM/RW | F/A(32s) | CF | SF/GM | KM/RW
[5 empty] | 10.5.07 | 18.6.07 | 04.07.07 | 6.8.07 | 21.5.07 | 25/6/07 | 04.07.07 | 6.8.07
| R1 | CER12 | FM/AR | 9.5.07 | R1 | CER14 | FM/AR | 9.5.07 | R2 | FER11 | MV/RM | 23.4.07
15 | F/A(17s) | KM GRRG | SF/GM | KM/TS/RW | F/A(16s) | KM | SF/GM | KM | F/A(24s) | OM/NB | SF/GM | KM/RW
| 21.5.07 | 15.6.07 | 04.07.07 | 6.8.07 | 10.5.07 | 15.6.07 | 04.07.07 | 1.8.07 | 21.5.07 | 19.06.07 | 04.07.07 | 6.8.07
ECS1 and ECS 2 swapped, labels corrected
| R2 | FER 24 | ? | ? |  |  |  |  | R2 | FER28 | S+G | 03.5.07
13 | F/A(18s) | CF+FE | SF/GM | KM/TS/RW |  |  |  |  | F/A(24s) | OM | SF/GM | KM/RW
| 21.5.07 | 2007-10-07 | 04.07.07 | 1.8.07 |  |  |  |  | 21.5.07 | 19.06.07 | 04.07.07 | 6.8.07
Note on C6: CF : GYGG < 15 Hz @ 8 fC < 400 Hz @ 7 fC
Note on C14: ECS cables swapped on chamber -> changed labels on SB side 1st half (FEB00-05):GRGG: O.K. (retesting without any change) ERROR: iFEB:1 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE! 5fC: 10^2 Hz 6fC: ~0 Hz 2nd half (FEB06-11):GYGG: O.K. noise: 5fC: <10^2Hz OLD (14.6.07) :1st half (FEB00-05):GRRG FEB03 (SG04) broad raw noise distribution Noise BAD: at 5fC -> 10^6 Hz 6fC: 10^3 Hz
Note on C17: LV-4(0/1) IB-1(1/2/3/10/11/12)
Note on C18: CF : GYYY repaired SG cable on chamber side < 20 Hz @ 8 fC ; < 1.1 kHz @ 7 fC
Note on E6: overlap in x O.K./ but not aligned in X wrt plumb
Note on E14: overlap in x O.K./ but not aligned in X wrt plumb
Note on E18: overlap in x O.K./ but not aligned in X wrt plumb
Note on H10: 1st half: GYGG noise: (after switch OFF anf ON LV) 5fC: 10^3Hz (FEB00), all others <10^2Hz 6fC: 10Hz (FEB00), all others: ~0Hz 2nd half: GYGG noise: 5fC: 10^2Hz 6fC: ~0Hz
Note on H14: FEB09 (SG10): ch4/5 contact problem on TB board: took out board, moved connector, and then Injection test had green light -> problem might come back in future 1st half (FEB00-05): after switching OFF anf ON HV and LV: GGYG ----------------------------------------------------- ----- Noise Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:20 I2C:1 FEB:4 CH:16 Estimated capacitance = 17 Cexp +- sigma = 49 +- 9 Channel estimated capacitance is out of range Estimated capacitance is lower than expected Noise: 5fC:10^2Hz 6fC:~0Hz 2nd half (FEB06-11): GRGG ----------------------------------------------------- ----- Offset Analysis Diagnostics ERROR: iFEB:1, 5 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE! Noise: 4fC:10^4Hz 5fC:10^2Hz 6fC:~0Hz
Note on J14: not aligned in X
Note on M6: CF : GYGY < 25 Hz @ 8 fC < 1200 Hz @ 7 fC
Note on M10: CF : GYGY < 100 Hz @ 8 fC; < 4 kHz @ 7 fC ----> found missing pins in TB crate & repaired (Nikolai, 22/6)
Note on M14: GRGY ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- ERROR: iFEB:0 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE! ERROR: iFEB:1 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE! ERROR: iFEB:2 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE! ERROR: iFEB:3 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE! ERROR: iFEB:4 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE! ERROR: iFEB:5 -> Database Offset does not match with Threshold Scan Offset CHECK BARCODE! ----------------------------------------------------- ----- Charge Analysis Diagnostics ----------------------------------------------------- WARNING: NodeID:20 I2C:2 FEB:0 CH:05 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 1156 WARNING: NodeID:20 I2C:2 FEB:0 CH:07 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 2920 WARNING: NodeID:20 I2C:2 FEB:4 CH:07 Threshold(fC): 7.0 (Resbias = 3.9) Noise Rate(Hz): 2761
Note on M15: LV 3/18,19 M4A-DW-IB-3-1,2,3,10,11,12
Note on M18: GYGG ----------------------------------------------------- ----- Offset Analysis Diagnostics ----------------------------------------------------- WARNING: iFEB:0 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:1 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:2 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:3 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:4 -> Barcode not found in database please confirm if barcode is correct WARNING: iFEB:5 -> Barcode not found in database please confirm if barcode is correct
Note on M19: LV 4/2,3 M4A-DW-IB-2-1,2,3,10,11,12